## Sheet1
Requirements |  | Sprint Backlog #1 - 2 Weeks
1 | Register new products to the inventory | Task | Mon | Tues | Wed | Thur | Fri
2 | View Inventory | Code user interface | 2 | 2
3 | Delete items from inventory | Code input form | 2 | 2
4 | Add photos for products (optional for users) | Code inventory view page using a table |  |  | 2 | 2
5 | Remind user of items purchased 2weeks+ ago
6 | Sign up page | Sprint Backlog #2 - 2 Weeks
7 | Log In page | Task | Mon | Tues | Wed | Thur | Fri
|  | Code login page | 3
|  | Code signup page |  | 3
|  | Add photo option |  |  | 2 | 2
|  | Remind user of old inventory |  |  |  | 2 | 2