## Sheet1
Requirements |  | Sprint Backlog #1 - 2 Weeks
1 | Register new products to the inventory | Task | Mon | Tues | Wed | Thur | Fri
2 | View Inventory | Code user interface | 2 | 2
3 | Delete items from inventory | Code input form | 2 | 2
4 | Add photos for products (optional for users) | Test case 1 |  | 1
5 | Remind user of items purchased 2weeks+ ago | Code inventory view page using a table |  |  | 2 | 2
6 | Sign up page | Test case 2 |  |  | 2
7 | Log In page | Test case 3 |  |  |  | 2
Sprint Backlog #2 - 2 Weeks
Test Cases |  | Task | Mon | Tues | Wed | Thur | Fri
1 | User must be able to register new products to the inventory | Code login page | 3
2 | User must be able to view inventory | Code signup page |  | 3
3 | User must be able to delete items from inventory | Add photo option |  |  | 2 | 2
4 | User must be able to sign up | Remind user of old inventory |  |  |  | 2 | 2
5 | User must be able to login | Test case 1 |  | 2
|  | Test case 4 |  |  | 2