## Sheet1
Requirements |  | Sprint Backlog #1 - 2 Weeks | [5 empty] | A | 2.4 | E=a(KLOC)^b | Effort | 0.55982 | PM
1 | Register new products to the inventory | Task | Mon | Tues | Wed | Thur | Fri | KLOC | 0.25 | D=c*E^d | DevTime | 2.006 | Months
2 | View Inventory | Code user interface | 2 | 2 |  |  |  | B | 1.05 | SS=E/D | StaffSize | 0.269 | Persons
3 | Delete items from inventory | Code input form | 2 | 2 |  |  |  | D | 0.38 | P=KLOC/E | Prod | 0.446 | KLOC/Person
4 | Add photos for products (optional for users) | Test case 1 |  | 1 |  |  |  | C | 2.5
5 | Remind user of items purchased 2weeks+ ago | Code inventory view page using a table |  |  | 2 | 2
6 | Sign up page | Test case 2 |  |  | 2 |  |  | .25^1.05 | 0.23326 | E^d = 0.802
7 | Log In page | Test case 3 |  |  |  | 2 |  | .23326 * 2.4 | 0.55982
Sprint Backlog #2 - 2 Weeks
Test Cases |  | Task | Mon | Tues | Wed | Thur | Fri
1 | User must be able to register new products to the inventory | Code login page | 3
2 | User must be able to view inventory | Code signup page |  | 3
3 | User must be able to delete items from inventory | Add photo option |  |  | 2 | 2
4 | User must be able to sign up | Remind user of old inventory |  |  |  | 2 | 2
5 | User must be able to login | Test case 1 |  | 2
|  | Test case 4 |  |  | 2
BASIC
Effort(E) = ab * (KLOC)^bb(in Person-months)
DevelopmentTime(D) = cb * (E)^db (in month)
Average staff size(SS) = E/D (in Person)
Productivity(P) = KLOC / E (in KLOC/Person-month)